## Action items
ASLA Action Items |  |  |  |  | Last Updated: February 12, 2007
Item Nbr | Item Description | Responsible | Status | Date Due | Notes
1 | Discuss w/ Keith Furnas (1) Vet soccer fields & re-crowning | Mike L. | Closed |  | Discussed w/ Keith
2 | Discuss w/ Keith Furnas - Collaborative projects with Little League | Bill | Closed |  | 6/5 - LL has issues getting volunteers. So does ASLA. Can we help each other? Keith is open to this. Need to meet - Keith & Bill
3 | Discuss w/ Keith Furnas - potential Kathy Furnas - Uniform Manager for ASLA? | Mike L. | Closed |  | Per Mike Musser - Leisa Wetzig is interested in this. Mike M & Mike L to follow-up w/ Leisa.
4 | Derive position descriptions & post openings on ASLA website | Tony | Closed |  | Positions to detail: +Rec Director +Boosters President +Concessions Manager +Referee Director
5 | ASLA Check cutting procedure – revise | Ron | Closed |  | 6/5 - Ron delivered this in May
6 | ASLA Travel Policy revision – route & recommend | Mike G. | Open | 2007-01-01 | 2/12 - Mike to resend updates to team 12/6 - Mike to propose travel policy & distribute to board members by Jan-1 11/1 - Needs modification to reflect U8 Travel, Coach Selection & Evaluation, & Player Evaluation Process 6/5 - Leave open as we may want to allow Boys' travel in the spring of their U8 year. Discussed on 3/1/06 meeting; Many concerns exist on this policy; All agreed to table this for now. No date identified for follow-up.
7 | Schedule (2) 12-14 coaches for Feb-24 – Mar-24 coaching clinic ($25/coach) | Mike L. | Closed |  | Clinic scheduled
8 | Work w/ Trina on ASLA New Coach Introduction Manual | Mike L. | Closed | 2006-07-15 | 6/5 - Mike's summer project... No update
9 | Schedule AHS & ASLA Travel Coach mtg (videos, pizza, beer) | Mike L. | Closed |  | Meeting scheduled - 3/21/06
10 | Troubled coaches meeting | Tony | Closed |  | 03/30 - Tony addressed this;
11 | U8 Development - communicate to U8 coaches (girls?) | Mike L. | Closed |  | Drafted communication. Need to review w/ Mike Besu; Lawler sent to coaches on 3/22.
12 | U8 Coaches meeting - Travel awareness? | Mike L. | Closed |  | 6/5 - Travel Soccer overview document posted on web
13 | Coordinate & communicate end-of-season equipment return | Mike M. | Closed |  | 6/5 - Mike Musser communicated to ASLA rec.
14 | Communicate procedure for working with Community Resource Services [Eligibility screening for ASLA scholarships] | Mike L. | Closed |  | Discussed w/ CRS (3/7/06). Their recommendation is to NOT publicize this as word will get out and our allotted scholarships will be consumed. Keep process internal to ASLA.
15 | Distribute # teams & coaches to Kevin D & Mike M | Tony | Closed
16 | Deliver Rec schedules to ASLA and Pablo | Kevin D | Closed
17 | Obtain & deliver Coach's equipment to new coaches | Mike M. | Closed
18 | Measure & mark ASLA fields | Bill | Closed |  | Also, let Mike L & Kevin M know so they can schedule Fields Crew
19 | Setup goals / nets | Kevin M | Closed
20 | Deliver Soccer Rock | Mike L. | Closed |  | Jerry Galant coordinated w/ a local contractor to donate & deliver the rock.
21 | Develop an ASLA Supplier database | Bill | Closed | 2006-07-15 | 2/12 - Done 12/6 - Bill to handle this 11/1 - No update 6/5 - Provide a single repository of the different vendors that ASLA uses including contacts, address, phone, email, product, cost, etc.
22 | Improve ASLA Travel Soccer Evaluations | Mike G. | Open | 2007-01-30 | 2/12 - Mike to resend to group 12/6 - Mike to make recommendations for improving evaluations by Jan-30 11/1 - No update 6/5 - Need to possibly move these to weekends in May.
23
24
25
26
27
23 | Revise Secretary Role | Tony | Closed | 2006-11-01 | 11/1 - Need board approval on this change 10/6 - Responsibilities: +Create binder of all policies and procedures +Assemble list of vendors +Take minutes at meetings +Communicate meeting times/business issues
24 | Define & Fill Marketing Role | Tony | Closed | 2006-01-15 | 2/12 - Jeanie is assuming these responsibilities 12/6 - Defined, but not filled --> combine this with the Registrar role for now 11/1 - Need board approval on this change 10/6 - Responsibilities: +Promote all facets of registration to public +School Distribution +Yard Signs +City Website +Forms to Donna +Press Release in Paper
25 | Implement On-Line Registration | Kevin | Closed | 2007-01-01 | 11/1 - Kevin provided recommendation. Demo to be setup by Dec-1 10/6 - Kevin to make recommendations on Nov-1
26 | Define ASLA Spring timeline | Tony | Closed | 2006-11-01 | 11/1 - WK1 - Apr-12 - Apr-14 WK2 - Apr-19 - Apr-21 WK3 - Apr-26 - Apr-28 WK4 - May-3 - May-5 WK5 - May-10 - May-12 WK6 - May-17 - May-19 WK7 - May-24 - May-25 (only Thurs & Fri) WK8 - May-31 - Jun-2 10/6 - Registration Start & End Dates; Assign tasks to Geeva for completion
27 | Create Travel Coach Selection and Evaluation Process | Mike G. | Open | 2007-01-01 | 2/12 - Mike to resend 12/6 - Mike to define & route to board 11/1 - No update
28 | Create U8 Travel Policy | Mike G. | Closed | 2006-11-01 | 12/6 - Closed as this is rolled into action item #6 11/1 - Mike G's developd a draft. Need to finalize.
29 | Define Travel Uniform Policy | Tony | Open | 2007-01-15 | 2/12 - Need to finalize uniform policy 12/6 - Uniform style/color selected; Need to formalize the process/policy 11/1 - Mike contacted Andy Karl on this. A couple of styles are available. Need to finalize ASLA's requirements by Jan-1. 10/13 - Tony & Mike to meet w/ Adidas supplier, discuss needs & define plan
30 | Finalize Decision on Travel Coaches' shirts | Mike G. | Closed | 2006-11-01 | 12/6 - Mike to purchase Adidas shirts from Tony's girl 11/1 - Mike G. to collaborate with Tony & Mike on vendor 10/13 - What are we buying & when?
31 | Identify Trophy / Picture Coordinator | Tony | Open | 2007-04-01 | 12/6 - low priority right now 11/1 - In progress
32 | Determine path forward for Rec uniforms | Geeva | Open | 2007-04-01 | 12/6 - low priority right now 11/1 - No update 10/13 - New Jersey? Add socks and shorts (mandatory or optional)
33 | Schedule End-of-Fall Season Celebration | Tony | Closed | 2007-01-15 | 12/6 - Scheduling for January-2007 11/1 - Tony to get this rolling. 10/13 - When? Where? Who?
34 | Define Fundrasing Event | Tony | Open | 2007-04-01 | 2/12 - no update 11/1 - No update 10/13 - Spring - Night at the races? It can be 100% outsourced and we can focus on selling tickets Goal to raise 10K min For what purpose?
35 | Collect outstanding Travel Player fees | Ron | Open | 2007-02-28 | 2/12 - Down to $5K; Jeanie to resend notification to coaches 12/6 - Still significant fees outstanding; Players will not be permitted to play if they have not paid 11/1 - In progress. 10/13 - Grudzien communicated status of travel player fees to all coaches. Ron to track progress.
36 | Obtain Contribution from FocusOne | Mike | Closed | 2006-11-01 | 11/6 - Contacted Alan. Check will be sent this week.
37 | Post & Maintain Referee schedules on Web-Site | Randy | Open | 2007-03-01 | 2/12 - Kevin to schedule & post schedules on-line; Refs will have to reschedules on their own 12/6 - Kevin investigating the opportunity; 11/1 - Concern about youth information on web-site. Need to investigate secure login to display & update.
38 | Remove U5 nets | Mike / Tony Brooks | Open | 2006-11-28 | 2/12 - no update
39 | Define what Indoor Soccer is for ASLA | Geeva | Open | 2007-01-01 | 2/12 - no update
40 | Develop program for General Footskills for off-season (winter) | Chris D | Open | 2007-09-01
41 | Determine if ASLA needs to have hard-copy of waiver form in addition to the coach having one | Kevin G. | Open | 2007-01-01 | 2/12 - OYSAN to allow this; Kevin to set this up for fall registration
42 | Arrange for AHS Varsity field use for Spring-2007 | Bill | Open | 2007-02-01 | 2/12 - AHS field & Village; Bill to follow-up w/ permits
43 | Acquire Rec Uniforms for Spring season | Geeva | Open | 2007-01-15 | 2/12 - Geeva to order at end of February
44 | Order U5 net clips | Mike L. | Open | 2007-01-15
45 | Order U6 nets | Mike L. | Open | 2007-01-15
46 | Analyze Travel & Rec fees | Ron | Open | 2007-04-01 | 2/12 - Follow-up w/ Ron
47 | Develop better method to track referee games & improve payment turnaround | Randy B | Open | 2007-03-15 | 2/12 - Multiple ideas tossed around. Randy to work w/ sub-team to identify best policy 12/6 - Ron to help Randy with this
48 | Identify start of fall registration | Jeanie | Open | 2007-04-01 | 2/12 - need to register kids before travel eval
49 | Poll 5 area communities to determine Rec & Travel fees & what is provided | Mike B | Open | 2007-03-01
Open
Open
Open